## Slide 1
STRATEGIC PLAN
FY12 - FY15
Department of Medicine
at the University at Buffalo
School of Medicine and Biomedical Sciences

## Slide 2
Strategic Planning Process 2
Mission, Vision and Goals 4
Strategies and Tactics 7
Implementation Plan 56
Appendices 60
Page
Contents

## Slide 3
I. STRATEGIC PLANNING PROCESS

## Slide 4
Strategic Planning Process
Planning Interviews
Stakeholder Survey on Strategic Priorities
Environmental Assessment
Define Departmental Vision
Define Goals with Measurable Outcomes
Develop Specific Strategies & Tactics
Finalize the Strategic Plan
Develop Implementation Plan with Target Dates and Assignments
PHASE I
Planning Research
PHASE II
Define
Strategic Direction
PHASE III
Finalize the Plan
The strategic planning process utilized a three-phased approach with specific tasks assigned to each phase. The conclusions drawn from each phase established the foundation of planning for each of the subsequent phases.
Notes: Strategic Planning Process:
(Most of the discussion can focus on what’s illustrated in this slide.)
Five distinct phases for completing the strategic plan, each of which builds upon the work completed in the previous phase. (We are currently in Phase III as illustrated above.)
Each phase also has a concrete timeline (to be discussed in the next slide).
Deliverables (as illustrated) are also defined for each phase so that each participant knows what to expect throughout the process.
The process is ultimately linked to the budget and annual management planning for implementation.

## Slide 5
II. MISSION, VISION & GOALS

## Slide 6
University at Buffalo School of Medicine & Biomedical Sciences
  To advance health and wellness across the life span for the people of New York and the world through the education of tomorrow’s leaders in health care and biomedical sciences, innovative research and outstanding clinical care.
Mission Statement:

## Slide 7
Vision and Goals:
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.
Goal 2: Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates.
Goal 3: Expand clinical and translational research.
Goal 4: Attract and retain talented faculty and staff to support all mission areas.
Goal 5: Forge a strong departmental identity founded on excellence, collaboration and innovation.
Goal 6: Develop a sound business model to provide sustainable resources to achieve our vision for the future.
UBMD Internal Medicine VISION Become a premier Department of Medicine among public institutions, achieving a level of excellence that will serve as a magnet for the regional community and distinguish the department nationally.

## Slide 8
STRATEGIES AND TACTICS

## Slide 9
Goals | Strategies
1. Strategically build a clinical practice that will be known as a major provider of excellent clinical care. | 1.1: Develop a superior patient-centered clinical practice.
 | 1.2: Expand selected subspecialty clinical services.
 | 1.3: Cultivate a strong network of primary care and specialty practices.
 | 1.4: Lead Western New York in the transformation of health care delivery systems.
2. Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates. | 2.1: Strengthen the quality and effectiveness of educational programs.
 | 2.2: Recruit and retain outstanding candidates for residency and fellowship programs.
 | 2.3: Create innovative educational programs for developing master clinicians and clinician researchers of the future.
3. Expand clinical and translational research. | 3.1: Select and systematically build interdisciplinary thematic areas of research.
 | 3.2: Promote investigator-initiated and industry-sponsored clinical trials.
 | 3.3: Institute strong partnerships across the School of Medicine, UB and the community to build unique strengths in research.
Goals with Supporting Strategies

## Slide 10
Goals | Strategies
4. Attract and retain talented faculty and staff to support all mission areas. | 4.1: Recruit and retain outstanding faculty to develop selected research and clinical areas and support outstanding educational programs.
 | 4.2: Recruit, retain and develop staff of the highest caliber.
 | 4.3: Invest in department-wide faculty development.
5. Forge a strong departmental identity founded on excellence, collaboration and innovation. | 5.1: Foster excellent relationships with our hospital partners so that the Department is viewed as the provider of choice for existing and new inpatient and outpatient services.
 | 5.2: Develop a new organizational model for the department and the practice plan.
 | 5.3: Increase local, national and international visibility.
6. Develop a sound business model to provide sustainable resources to achieve our vision for the future. | 6.1: Develop and implement a straightforward, productivity-based faculty compensation plan.
 | 6.2: Institute business standards and practices to improve financial stewardship.
 | 6.3: Pursue development opportunities.
Goals with Supporting Strategies (cont’d)

## Slide 11
Goals | Strategies
1. Strategically build a clinical practice that will be known as a major provider of excellent clinical care. | 1.1: Develop a superior patient-centered clinical practice.
 | 1.2: Expand selected subspecialty clinical services.
 | 1.3: Cultivate a strong network of primary care and specialty practices.
 | 1.4: Lead Western New York in the transformation of health care delivery systems.
Goal 1. Detailed Strategies and Tactics

## Slide 12
Strategy 1.1
Develop a superior patient-centered clinical practice.
Preliminary Tactics:
  Create a culture where every member of the clinical team recognizes the importance of the patient and family experience.
    Regularly measure and report on patient satisfaction in all settings.
    Provide customer service training for all faculty and staff.
  Implement efficient scheduling systems for patients and referring physicians.
    Implement a central scheduling service/number for patients and referring physicians.
    Create patient and physician website portals.
    Offer “One Stop Shopping” services for labs and diagnostics.
  Evaluate use of electronic media to increase the success of patient education.
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.

## Slide 13
Strategy 1.1
Develop a superior patient-centered clinical practice. (cont’d)
Preliminary Tactics:
  Adopt performance standards to address:
    Hours of operation;
    Cancellations and changes to clinic schedules;
    Turnaround time for call-backs to patients and referring physicians;
    Number of patient visits per clinic session;
    Guidelines for scheduling acute care and well-visit appointments; and
    Patient satisfaction.
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.

## Slide 14
Strategy 1.2
Expand selected subspecialty clinical services.
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.
Preliminary Tactics:
  Grow selected subspecialty programs identified using a criteria-based assessment. (See Appendix A for criteria-based scoring)
Primary Care
General Internal Medicine
Geriatrics
Medicine-Pediatrics
Infectious Disease
Oncology
Allergy, Immunology, Rheumatology
Palliative Medicine
Hematology
Clinical Pharmacology
Programs Targeted for Growth
Cardiovascular
Endocrinology and Metabolism
Nephrology
Pulmonary, Critical Care and Sleep Medicine
Gastroenterology, Hepatology, and Nutrition
Programs Targeted for Maintenance

## Slide 15
Expand selected subspecialty clinical services. (cont’d)
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.
Preliminary Tactics:
  Provide additional resources as follows to grow identified clinical subspecialties.*
Cardiovascular
Faculty** | Staff | Space | Equipment/Other
Electrophysiologist (VA) Interventional Cardiologist (BGH/VA) Director of Electrophysiology Program Director (General Cardiologist) Director Women’s Heart program (BGH) General Cardiologist (Outreach Program) | 1 NP/PA Administrative Assistant | Ambulatory office space downtown Clinical faculty office space (6 offices 2 support) | Ambulatory Clinical Digital image archive for practice (PACS) – Ambulatory ECG Tilt table capability Stress echo and reading stations Interfaces for image reporting with Allscripts 2nd Site Stress lab Nuclear lab Echo lab Outpatient 3T MRI Inpatient Clinical (VA & KH) PET/CT Cardiac MRI Cardiac CT Dedicated VA EP lab
Strategy 1.2
* Preliminary suggestions to be evaluated through business planning as described in 1.2.c
** Links to summary of faculty recruitment by division outlined in Strategy 4.1 and Appendix C.

## Slide 16
Strategy 1.2
Expand selected subspecialty clinical services. (cont’d)
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.
Preliminary Tactics:
  Provide additional resources as follows to grow identified clinical subspecialties.*
Endocrinology
and Metabolism
Faculty** | Staff | Space | Equipment/Other
2 Clinician Researchers |  |  | 
Transplant Nephrologist General Nephrologist, clinical & research General Nephrologist | 1 PA for dialysis | New infusion unit (could be developed in collaboration with other department or divisions) Clinic for remote post transplant and CKD patients | Telemedicine capabilities to expand geographic reach
Nephrology
* Preliminary suggestions to be evaluated through business planning as described in 1.2.C.
** Links to summary of faculty recruitment by division outlined in Strategy 4.1 and Appendix C.

## Slide 17
Strategy 1.2
Expand selected subspecialty clinical services. (cont’d)
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.
Preliminary Tactics:
  Provide additional resources as follows to grow identified clinical subspecialties*. (cont’d)
Faculty** | Staff | Space | Equipment/Other
Critical Care Clinician Educator (BGH) | 0.5 FTE Administrative Support (BGH) |  | New pulmonary equipment for the Dent practice Funding to develop a marketing program
Clinical faculty (ECMC) Clinical faculty (senior) for GI (BGH) (hepatologist) Clinical faculty (junior) for GI services (BGH) | 1 NP/PA |  | ECMC should update endoscopy unit GI motility equipment
Pulmonary, Critical Care and Sleep Medicine
Gastroenterology, Hepatology, and Nutrition
* Preliminary suggestions to be evaluated through business planning as described in 1.2.C.
** Links to summary of faculty recruitment by division outlined in Strategy 4.1 and Appendix C.

## Slide 18
Strategy 1.2
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.
Preliminary Tactics:
  Use a standardized business planning template for thorough, detailed assessment of clinical program investment that includes:
    Program description;
    Target market and assessment of competition;
    Identification of internal and external participants;
    Management and operations; and
    Financial model and projected return on investment.
Expand selected subspecialty clinical services. (cont’d)

## Slide 19
Strategy 1.3
Cultivate a strong network of primary care and specialty practices.
Preliminary Tactics:
  Explore various options to expand general medicine and medicine-pediatric primary care base:
    Develop innovative approaches to recruit new General Internal Medicine faculty given persistent workforce shortages.
    Expand the use of mid-level providers.
    Develop an affiliate network.
      Identify potential practices that would be interested in affiliation.
      Examine other successful models employed elsewhere.
      Offer practice management services and access to EMR.
    Develop a Federally-Qualified Health Center (FQHC) run by the Department.
    Collaborate with other UB departments that offer primary care services.
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.

## Slide 20
Strategy 1.3
Cultivate a strong network of primary care and specialty practices. (cont’d)
Preliminary Tactics:
  Expand subspecialty care referrals.
    Ensure referrals are captured from within the department and from other UB departments.
      Train Dent staff to refer internally.
      Market subspecialty services directly to referring physician office staff.
    Cultivate relationships with community primary care providers.
      Track referral volume and recognize high-volume referrers.
      Query referring physicians to assess service and access needs.
    Offer robust inpatient consultation and management services.
  Develop an inpatient hospitalist service.
    Work with surgeons and hospitals to determine how best to meet their needs.
    Build upon successful hospitalist services currently offered by pediatricians and geriatricians.
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.

## Slide 21
Strategy 1.3
Cultivate a strong network of primary care and specialty practices. (cont’d)
Preliminary Tactics:
  Explore opportunities to expand Department’s presence in outlying areas, such as:
    South Towns;
    North area; and
    East area.
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.

## Slide 22
Strategy 1.4
Lead Western New York in the transformation of health care delivery systems.
Preliminary Tactics:
  Participate in evaluating the creation of Accountable Care Organizations (ACOs) for the Buffalo market.
  Develop patient-centered medical home practices.
  Develop productivity measures that will ensure efficiency and address payment reform.
  Position the Department /School to participate in health reform demonstration projects.
    Obtain National Committee for Quality Assurance (NCQA) certifications to secure health care reform funding.
    Ensure that electronic health records are designed to demonstrate meaningful use.
    Develop a clinical model that is aligned with pay for performance criteria.
Goal 1: Strategically build a clinical practice that will be known as a major provider of excellent clinical care.

## Slide 23
Goal 2. Detailed Strategies and Tactics
Goals | Strategies
2. Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates. | 2.1: Strengthen the quality and effectiveness of educational programs.
 | 2.2: Recruit and retain outstanding candidates for residency and fellowship programs.
 | 2.3: Create innovative educational programs for developing master clinicians and clinician researchers of the future.

## Slide 24
Strategy 2.1
Strengthen the quality and effectiveness of educational programs.
Preliminary Tactics:
  Develop unified and consistent residency experiences across sites.
    Insure that goals and objectives for each rotation are understood by teaching faculty.
    Develop uniform standards for training.
  Evaluate the impact of decreasing the size of the training program; consider:
    Quality of the residents recruited;
    Future physician manpower needs in Western NY; and
    Departmental faculty recruitment plans.
  Improve faculty effectiveness.
    Increase faculty attendance at resident teaching conferences.
    Incorporate educational performance measures into promotion requirements.
    Recognize and reward high-quality voluntary faculty.
  Develop a mentoring program for the residents.
Goal 2: Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates.

## Slide 25
Strategy 2.2
Recruit and retain outstanding candidates for residency and fellowship programs.
Preliminary Tactics:
  Strengthen departmental interactions with medical students to identify the best candidates for recruitment into the residency program.
    Ensure the department offers a sufficient number of electives.
    Refine electives to include experiences at outpatient sites.
    Allow students from other medical schools to take electives in the Department.
    Assess and improve student experiences in clinical modules.
    Emphasize clinician educator and physician scientist experiences.
  Encourage yearly participation in the Empire Clinical Research Investigator Program.
  Leverage competitive fellowship programs to increase the quality of the general medicine applicant pool.
    Offer combined fellowship and residency programs to outstanding candidates.
      Secure funding to support research time.
Goal 2: Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates.

## Slide 26
Strategy 2.2
Recruit and retain outstanding candidates for residency and fellowship programs. (cont’d)
Preliminary Tactics:
  Restructure the resident recruitment and interview process.
    Complete departmental web redesign project and update regularly.
    Canvas current residents for likes/dislikes of existing interview schedule.
    Restructure the interview schedule for prospective residents.
      Include tours of all major teaching hospitals and Buffalo.
      Describe new master clinician and clinician researcher tracks; develop brochures, etc.
      Resolve scheduling conflicts of simultaneous division and general medicine interviews.
  Use social media to attract residents.
  Strengthen interactions with Caribbean and Osteopathic schools.
  Create community medicine and international medicine experiences in the program.
Goal 2: Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates.

## Slide 27
Strategy 2.3
Create innovative educational programs for developing master clinicians and clinician researchers of the future.
Preliminary Tactics:
  Track I: Master Clinician
    Develop a curriculum for master clinicians to emphasize broad-based clinical skills in outpatient and inpatient medicine.
    Build the ambulatory training experience around the patient-centered medical home instead of hospital-based clinics.
    Evaluate existing models of successful master clinician residency programs ( e.g., University of Rochester Medical Center).
    Match individual residents with faculty mentors.
    Provide development opportunities to ensure that faculty are prepared to facilitate the master clinician track.
Goal 2: Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates.

## Slide 28
Strategy 2.3
Create innovative educational programs for developing master clinicians and clinician researchers of the future. (cont’d)
Preliminary Tactics:
  Track II: Clinician Researcher
    Formalize the research track as a clearly recognized, structured offering for residents.
    Hold an annual department research day to highlight the research of residents and fellows.
    Increase the number of departmental research seminars.
    Identify faculty with active research programs to mentor trainees.
    Recruit residents and fellows who are interested in research fellowships.
    Identify new sources of funding to support both U.S. citizen and non-citizen trainees.
      Increase the number of K30 awards.
      Identify potential donors.
    Link the clinician researcher track to the CTSA.
  Explore the development of new master’s programs or joint degrees in business and clinical research to complement the existing joint program in public health.
Goal 2: Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates.

## Slide 29
Goal 3. Detailed Strategies and Tactics
Goals | Strategies
3. Expand clinical and translational research. | 3.1: Select and systematically build interdisciplinary thematic areas of research.
 | 3.2: Promote investigator-initiated and industry-sponsored clinical trials.
 | 3.3: Institute strong partnerships across the school of medicine, UB and the community to build unique strengths in research.

## Slide 30
Preliminary Tactics:
  Organize around and invest resources in the following research focal points identified using a criteria-based assessment.*
Cross-Cutting Research Approaches (blue)
Disease-Based Focal Points (yellow)
Clinical and Translational Research
Health Services Research (Patient Safety, Cost Effectiveness, Outcomes)
Metabolic Disorders
(Obesity, Diabetes,
Gastroenterology)
Chronic Disease Management (Cardiology, Nephrology)
Infectious Disease and Pulmonary
Strategy 3.1
Select and systematically build interdisciplinary thematic areas of research.
Goal 3: Expand clinical and translational research.
* See appendix B for detailed criteria-based assessment.

## Slide 31
Faculty** | Staff | Space | Equipment
Electrophysiologist Translational Research (MD) Director Advanced Imaging (PET/MRI) Clinical/Research Cardiac Stem Cell Biology/ NI cardiology physician scientist (MD or PhD) 2 Nephrology Physician Scientists | Administrative Assistant | New research faculty offices (7 office, 2 support) in CTRC Will relocate existing research faculty to the 7th floor CTRC - no renovation required. | Provided in the CTRC (see page 32)
Preliminary Tactics:
  Provide additional resources as follows to grow identified research focal points.*
Strategy 3.1
Select and systematically build interdisciplinary thematic areas of research. (cont’d)
Goal 3: Expand clinical and translational research.
Chronic Disease Management (Cardiology, Nephrology)
* Preliminary suggestions to be evaluated through business planning as described in 3.1.d
** Links to summary of faculty recruitment by division outlined in Strategy 4.1 and Appendix C.

## Slide 32
* Preliminary suggestions to be evaluated through business planning as described in 3.1.d
** Links to summary of faculty recruitment by division outlined in Strategy 4.1 and Appendix C.
Preliminary Tactics:
  Provide additional resources as follows to grow identified research focal points.*
Strategy 3.1
Select and systematically build interdisciplinary thematic areas of research. (cont’d)
Goal 3: Expand clinical and translational research.
Metabolic Disorders
(Obesity, Diabetes,
Gastroenterology
Infectious Disease and Pulmonary
Faculty** | Staff | Space | Equipment
2 Physician Scientists (Endocrinologists or Diabetologists) 2 Physician Scientists in GI (research areas TBD after clinical recruitments are completed) | 2 lab technicians (MS or BS) | 1000 NSF space for new hires 8000-9000 NSF clinical research space to replace existing space that is coming off line in 2012. Need to have enough space to house both the clinical and research functions together as is currently. | Department Shared Resources (See page 32)
Sleep Researcher PhD Researcher in COPD or Respiratory infections (VA) Physician Scientist in Interstitial Lung Disease or Asthma (BGH) Health Services Researcher (MD or PhD) Infectious Disease Clinical Translational or Bench Researcher (MD) | Clinical study coordinator (see page 32) | Lab space for 5 new hires Office and file space at Dent and Kaleida for clinical studies | TBD by new hires

## Slide 33
Preliminary Tactics:
  Provide additional resources as follows to grow interdisciplinary research approaches.*
Staff | Equipment
Trained Research Staff Shared Across the Department Clinical study coordinators to work with physicians to develop clinical research projects that could be integrated with the VA clinical research programs Clinical study coordinators to conduct physical assessments needed for clinical research Statistical support for research projects | Departmental Research Equipment Flow Cytometer Florescent microscope Research Equipment for CTRC Shared across departments and disciplines 3T MRI scanner 320 slice CT scanner Cyclotron and Radiochemistry Small animal fluorescence, bioluminescence imaging Rodent Echo Human echo Small animal MRI Small animal PET/SPECT/CT Multi-photon confocal microscope Animal implantable telemetry system Portable digital fluoroscopy for animal
Strategy 3.1
Select and systematically build interdisciplinary thematic areas of research. (cont’d)
Goal 3: Expand clinical and translational research.
Clinical and
Translational
Research
Health Services
Research
(Patient Safety,
Cost Effectiveness,
Outcomes)
* Preliminary suggestions to be evaluated through business planning as described in 3.1.d
  Links to Strategy 3.2

## Slide 34
Strategy 3.1
Select and systematically build interdisciplinary thematic areas of research. (cont’d)
Goal 3: Expand clinical and translational research.
Preliminary Tactics:
  Develop and implement sustainable business plans to ensure investments in proposed thematic areas are successful.
  Recruit and retain top-quality researchers. (Links to Strategy 4.1)
    Create an endowment to fund protected time for research.
    Recruit mid-level and senior research teams.
    Increase the number of basic scientists in the department.

## Slide 35
Strategy 3.2
Promote investigator-initiated and industry-sponsored clinical trials.
Goal 3: Expand clinical and translational research.
Preliminary Tactics:
  Lead SMBS in developing clinical trials for the region.
  Create a departmental clinical trials office.
    Hire a nurse coordinator and biostatistician.
    Provide seed grants to initiate new clinical trials.
    Develop a process to facilitate and expedite legal and IRB reviews.
  Develop a research database to facilitate internal and external collaboration.
  Collaborate with Preventive Medicine and Women’s Health to initiate new trials.
  Collaborate with referring physicians to provide clinical trials to their patients.

## Slide 36
Strategy 3.3
Institute strong partnerships across SMBS, UB and the community to build unique strengths in research.
Goal 3: Expand clinical and translational research.
Preliminary Tactics:
  Leverage SMBS investments in the Clinical and Translational Science Award (CTSA) program and research cores to enhance research in the department.
  Work with SMBS leadership and other SMBS departments to ensure access to expertise in the following disciplines:
    Informatics;
    Bioengineering;
    IT; and
    School of Pharmacy.
  Facilitate interdisciplinary collaboration across the department, SMBS and UB.
    Develop a research database that identifies areas of research by faculty member.
    Offer secondary appointments.
    Provide seed grants for novel collaborations.

## Slide 37
Goal 4. Detailed Strategies and Tactics
Goals | Strategies
4. Attract and retain talented faculty and staff to support all mission areas. | 4.1: Recruit and retain outstanding faculty to develop selected research and clinical areas and support outstanding educational programs.
 | 4.2: Recruit, retain and develop staff of the highest caliber.
 | 4.3: Invest in department-wide faculty development.

## Slide 38
Strategy 4.1
Recruit and retain outstanding faculty to develop selected research and clinical areas and support outstanding educational programs.
Goal 4: Attract and retain talented faculty and staff to support all mission areas.
Preliminary Tactics:
  Recruit faculty to support strategic growth, fill expected and existing vacancies: (Links to Strategy 1.2 and 3.1)
Refer to Appendix C for details

## Slide 39
Strategy 4.1
Recruit and retain outstanding faculty to develop selected research and clinical areas and support outstanding educational programs.
Goal 4: Attract and retain talented faculty and staff to support all mission areas.
Preliminary Tactics:
  Identify top residents and groom them as future faculty.
    Track where residents go following program completion to determine why they leave Buffalo.
  Supply bridge funding for start-up faculty programs.
  Implement a regular process for allocating and reappointing voluntary faculty. (Links to Strategy 2.2)
    Evaluate Harvard’s model for allocation of appointments.
    Establish evaluation criteria to ensure appointments result in meaningful contribution.
    Align promotion criteria for voluntary faculty and non-tenured faculty.

## Slide 40
Strategy 4.2
Recruit, retain and develop staff of the highest caliber.
Goal 4: Attract and retain talented faculty and staff to support all mission areas.
Preliminary Tactics:
  Increase recognition of departmental brand among prospective employees.
    Develop and communicate a “department story” about “what we do” (i.e. Fed Ex & Nike).
    Engage staff in promoting the “departmental story.”
  Construct a more functional and efficient departmental infrastructure.
  Align staff and faculty recruitment plans.
    Focus efforts where retention has historically been a problem.
  Evaluate compensation and benefit options; consider:
    Tuition reimbursement; and
    Loan forgiveness opportunities.
  Create opportunities for advancement.
    Provide regular in-service training.

## Slide 41
Strategy 4.2
Goal 4: Attract and retain talented faculty and staff to support all mission areas.
Preliminary Tactics:
  Provide opportunities for staff to participate in departmental/clinic decision-making such as:
    Implementing quality improvement initiatives;
    Creating customer service standards and practices; and
    Establishing accountability measures.
  Create a team identity.
    Host team building events.
    Invite staff to academic activities (journal club).
  Develop strategies to facilitate departmental communication across multiple sites.
    Regularly publicize departmental vision and strategic plan and progress in achieving the plan aims.
    Investigate the use of electronic communication methods, website, twitter and Facebook.
Recruit, retain and develop staff of the highest caliber. (cont’d)

## Slide 42
Strategy 4.3
Invest in department-wide faculty development.
Goal 4: Attract and retain talented faculty and staff to support all mission areas.
Preliminary Tactics:
  Develop a formal mentoring program for faculty; topics to be addressed should include:
    Best educational practices;
    Clinical research;
    Promotion process; and
    Grant writing.
  Encourage participation in the Royal College of Physicians program for faculty with substantial interest/assigned effort in education.
  Develop a transparent promotion process.
    Increase standards for promotion on the clinician educator track.
    Implement a regular faculty review program.
    Ensure that standards for scholarly activity for promotion are clear.
      Give credit for peer-reviewed curriculum development.

## Slide 43
Strategy 4.3
Invest in department-wide faculty development. (cont’d)
Goal 4: Attract and retain talented faculty and staff to support all mission areas.
Preliminary Tactics:
  Develop a recognition program to honor valued voluntary faculty.
  Nominate faculty for local and national awards.
  Establish a visiting professorship program.

## Slide 44
Goal 5. Detailed Strategies and Tactics
Goals | Strategies
5. Forge a strong departmental identity founded on excellence, collaboration and innovation. | 5.1: Foster excellent relationships with our hospital partners so that the Department is viewed as the provider of choice for existing and new inpatient and outpatient services.
 | 5.2: Develop a new organizational model for the department and the practice plan.
 | 5.3: Increase local, national and international visibility.

## Slide 45
Strategy 5.1
Foster excellent relationships with our hospital partners so that the Department is viewed as the provider of choice for existing and new inpatient and outpatient services.
Goal 5: Forge a strong departmental identity founded on excellence, collaboration and innovation.
Preliminary Tactics:
  Capitalize on the medical school’s downtown relocation to create an academic home for the department.
  Assess merging/reconfiguring ECMC, BGH, and Dent outpatient practices.
  Strengthen relationship with Roswell Park.
    Work with Roswell Park to create new clinical programs for oncology services at BGH and ECMC.
    Explore opportunities to provide non-oncology inpatient and outpatient coverage to Roswell Park patients.
    Expand research collaborations.
  Develop an inpatient hospitalist service and consult service for Kaleida Health. (links to Strategy 1.2)

## Slide 46
Strategy 5.1
Foster excellent relationships with our hospital partners so that the Department is viewed as the provider of choice for existing and new inpatient and outpatient services. (cont’d)
Goal 5: Forge a strong departmental identity founded on excellence, collaboration and innovation.
Preliminary Tactics:
  Assess developing needs for hospitalist, critical care, general medicine, and subspecialty care at ECMC and position the department to be the provider of choice.
  Pursue opportunities to become the outpatient service provider for the Great Lakes system.
  Continue to cultivate partnership with the VA that promotes research and education.

## Slide 47
Strategy 5.2
Develop a new organizational model for the department and the practice plan.
Goal 5: Forge a strong departmental identity founded on excellence, collaboration and innovation.
Preliminary Tactics:
  Form a strong and stable departmental leadership team within the department.
    Appoint a departmental Executive Council (see organization chart on the following slide).
    Amend practice plan bylaws to designate departmental Vice Chair for Clinical Affairs as a member of the UBMD Internal Medicine Board of Directors.
    Build a skilled practice plan management team.

## Slide 48
Chair
Clinical Divisions
Allergy, Immunology & Rheumatology
Clinical Pharmacology
General Internal Med
Hematology
Med/Peds
Nephrology
Palliative Care
Cardiology
Endocrinology
Geriatrics
Infectious Disease
Gastro-enterology
Oncology
Pulmonary/ Critical Care
Executive Council
VC Research
VC Faculty Development
VC Education
CPM2 Director
Clerkship Director
IM Resident Director
VC Clinical Affairs
UB/MD Practice Plan
CFO
Human Resources Manager
Comptroller
Practice Plan Admin.
University Administration
Executive Director
Staff Assistant
Admin Assistant
Admin Assistant
Executive Assistant
Strategy 5.2
Develop a new organizational model for the department and the practice plan. (cont’d)
Goal 5: Forge a strong departmental identity founded on excellence, collaboration and innovation.

## Slide 49
Strategy 5.3
Increase local, national and international visibility.
Goal 5: Forge a strong departmental identity founded on excellence, collaboration and innovation.
Preliminary Tactics:
  Re-brand the department as “UBMD Internal Medicine” and phase out AMS.
  Develop a marketing plan to communicate new departmental brand identity.
    Capitalize on being Buffalo’s only academic health center.
      Use clinical trials to differentiate UB Medicine from community providers.
    Promote the departmental vision and strategic plan.
    Become the public expert for health topics.
    Nominate faculty for Buffalo’s “Best Doctor Listing.”
    Invest in media training for faculty and staff.
    Collaborate with hospital and university PR programs.

## Slide 50
Strategy 5.3
Increase local, national and international visibility. (cont’d)
Goal 5: Forge a strong departmental identity founded on excellence, collaboration and innovation.
Preliminary Tactics:
  Promote faculty achievements.
    Nominate faculty for awards and honors throughout their careers.
      Identify and nominate faculty to the Institute of Medicine.
    Increase the number of faculty that participate on national committees.
  Promote continuing education courses to the community.

## Slide 51
Goal 6. Detailed Strategies and Tactics
Goals | Strategies
6. Develop a sound business model to provide sustainable resources to achieve our vision for the future. | 6.1: Develop and implement a straightforward productivity-based faculty compensation plan.
 | 6.2: Institute business standards and practices to improve financial stewardship.
 | 6.3 Pursue development opportunities.

## Slide 52
Strategy 6.1
Develop and implement a straightforward productivity-based faculty compensation plan.
Goal 6: Develop a sound business model to provide sustainable resources to achieve our vision for the future.
Preliminary Tactics:
  Evaluate successful compensation plans from other departments and divisions (e.g., Family Medicine, Surgery, Orthopedic Surgery and Neurosurgery).
  Identify data collection systems needed to measure productivity.
  Develop an annual review process that is tied to the departmental budget and strategic plan.
    Establish criteria for all three mission areas.
    Allow for a certain amount of discretion by chair and division chiefs.
    Identify funding for bonus pool.
  Ensure expectations are understood by faculty.
  Align productivity measurement practices with hospital partners.

## Slide 53
Strategy 6.2
Institute business standards and practices to improve financial stewardship.
Goal 6: Develop a sound business model to provide sustainable resources to achieve our vision for the future.
Preliminary Tactics:
  Improve systems to obtain accurate data in the following domains:
    Financial;
    Research;
    Space;
    Quality; and
    Clinical productivity.
  Effectively manage the revenue cycle.
  Regularly disseminate performance and benchmark data at the department, division and faculty levels.
    Distribute monthly management reports.
    Provide monthly reviews of billing, collections and RVUs.
    Phase-in data dissemination from blinded reporting to full disclosure.

## Slide 54
Strategy 6.2
Institute business standards and practices to improve financial stewardship. (cont’d)
Goal 6: Develop a sound business model to provide sustainable resources to achieve our vision for the future.
Preliminary Tactics:
  Ensure department is in compliance with regulatory and contractual relationships.
  Advocate for higher regional reimbursement rates.
  Implement an annual capital budgeting process.
  Develop departmental master facilities plan for clinical and academic programs based on the following elements:
Facility | Departmental Specifications | Resources
Life cycle cost of existing facilities Renovations vs. new construction Existing square footage Zoning Parking/transportation | Adjacency: IM divisions, SMBS departments, clinical partners, research programs & competition Increase in faculty and staff Increase in medical school class size Specialized facilities, classrooms, laboratories, clinical & research equipment Service area | Funding SMBS master planning Phasing plan for relocations Timing

## Slide 55
Strategy 6.3
Pursue development opportunities.
Goal 6: Develop a sound business model to provide sustainable resources to achieve our vision for the future.
Preliminary Tactics:
  Coordinate departmental fundraising with UB SMBS and UB.
  Leverage the creation of the Strategic Plan to highlight the department’s aspirations for the future.
    Create collateral material for donors based on the strategic plan.
  Create fundraising approaches targeted at different potential donor audiences as follows:
    Residency and fellowship program alumni;
    Medical School graduates;
    Grateful patients;
    Foundations; and
    Corporations.

## Slide 56
Strategy 6.3
Pursue development opportunities. (cont’d)
Goal 6: Develop a sound business model to provide sustainable resources to achieve our vision for the future.
Preliminary Tactics:
  Identify key programmatic needs to be supported through fundraising; consider:
    Endowed chairs in every division;
    Research endowment;
    Clinical centers of excellence; and
    Support for educational program development.
  Explore methods for development such as:
    Online donations
    Special events
    Research Day – invite donors/potential donors
  Consider development of a advisory board comprised of influential members of the Buffalo community.
    Build upon board member, faculty and staff connections to cultivate prospective donors.

## Slide 57
IV. Implementation Plan

## Slide 58
Measures of Success
 | Goals | Metrics
1 | Strategically build a clinical practice that will be known as a major provider of excellent clinical care. | Market share Patient satisfaction Number of new patients Professional fees Attainment of quality benchmarks (e.g. NCQA) Volume and dollar value of contracts
2 | Improve the quality and reputation of the residency and fellowship training programs in order to attract and retain the best candidates. | Full accreditation Trainee satisfaction Proportion of U.B. and U.S. medical school graduates Board passage rates Job placement of residents
3 | Expand clinical and translational research . | Research funding Departmental NIH ranking Number of faculty with funded research Clinical trials enrollment
4 | Attract and retain talented faculty and staff to support all mission areas. | Number of faculty Number of voluntary faculty appointments Staff and faculty turnover Length of time for recruitment Number of applications for positions
5 | Forge a strong departmental identity founded on excellence, collaboration and innovation. | Mentions in the popular press Number of referrals from outside of department Measured improvement in community perceptions Website hits
6 | Develop a sound business model to provide sustainable resources to achieve our vision for the future. | Attainment of financial targets Increase in RVUs/faculty Improved payer mix

## Slide 59
Prioritization and Strategy Champions

## Slide 60: Strategic Planning Steering Committee